## Gantt Chart
Phase | Task Name | Start Date | End Date | Duration (Days) | Start Offset | Duration
Phase 1: Research | Literature Review | 2025-03-01 | 2025-03-15 | 14 | 0 | 14
Phase 1: Research | Competitive Analysis | 2025-03-08 | 2025-03-22 | 14 | 7 | 14
Phase 1: Research | Requirements Gathering | 2025-03-15 | 2025-03-29 | 14 | 14 | 14
Phase 1: Research | Use Case Development | 2025-03-22 | 2025-04-12 | 21 | 21 | 21
Phase 2: Design | Architecture Design | 2025-04-13 | 2025-04-27 | 14 | 43 | 14
Phase 2: Design | Database Schema Design | 2025-04-20 | 2025-05-11 | 21 | 50 | 21
Phase 2: Design | UI/UX Design | 2025-05-04 | 2025-05-25 | 21 | 64 | 21
Phase 2: Design | API Endpoint Design | 2025-05-18 | 2025-06-08 | 21 | 78 | 21
Phase 2: Design | Integration Planning | 2025-05-25 | 2025-06-08 | 14 | 85 | 14
Phase 3: Backend | Dev Environment Setup | 2025-06-08 | 2025-06-15 | 7 | 99 | 7
Phase 3: Backend | Authentication System | 2025-06-15 | 2025-06-29 | 14 | 106 | 14
Phase 3: Backend | Core Models Development | 2025-06-22 | 2025-07-13 | 21 | 113 | 21
Phase 3: Backend | Business Logic Controllers | 2025-07-06 | 2025-07-27 | 21 | 127 | 21
Phase 3: Backend | Advanced Features | 2025-07-20 | 2025-08-10 | 21 | 141 | 21
Phase 3: Backend | Payment Integration | 2025-08-03 | 2025-08-24 | 21 | 155 | 21
Phase 3: Backend | Community Features | 2025-08-10 | 2025-08-24 | 14 | 162 | 14
Phase 3: Backend | Media Upload Integration | 2025-08-17 | 2025-08-24 | 7 | 169 | 7
Phase 4: Frontend | Landing & Auth UI | 2025-08-24 | 2025-09-07 | 14 | 176 | 14
Phase 4: Frontend | Course Catalog & Details | 2025-09-07 | 2025-09-21 | 14 | 190 | 14
Phase 4: Frontend | Dashboard Interfaces | 2025-09-14 | 2025-10-05 | 21 | 197 | 21
Phase 4: Frontend | Lesson & Quiz Interfaces | 2025-09-28 | 2025-10-19 | 21 | 211 | 21
Phase 4: Frontend | Payment & E-commerce | 2025-10-12 | 2025-10-26 | 14 | 225 | 14
Phase 4: Frontend | Community & Profile | 2025-10-19 | 2025-11-02 | 14 | 232 | 14
Phase 4: Frontend | UI/UX Polish | 2025-10-26 | 2025-11-09 | 14 | 239 | 14
Phase 5: Testing | Unit Testing | 2025-10-05 | 2025-10-26 | 21 | 218 | 21
Phase 5: Testing | Integration Testing | 2025-10-19 | 2025-11-02 | 14 | 232 | 14
Phase 5: Testing | Security Testing | 2025-10-26 | 2025-11-09 | 14 | 239 | 14
Phase 5: Testing | Performance Testing | 2025-11-02 | 2025-11-16 | 14 | 246 | 14
Phase 5: Testing | Cross-browser Testing | 2025-11-09 | 2025-11-23 | 14 | 253 | 14
Phase 5: Testing | User Acceptance Testing | 2025-11-16 | 2025-11-23 | 7 | 260 | 7
Phase 6: Refactoring | Create Firebase Helpers | 2025-10-19 | 2025-10-26 | 7 | 232 | 7
Phase 6: Refactoring | Build Missing Models | 2025-10-26 | 2025-11-02 | 7 | 239 | 7
Phase 6: Refactoring | Enhance Existing Models | 2025-10-26 | 2025-11-09 | 14 | 239 | 14
Phase 6: Refactoring | Fix N+1 Query Problems | 2025-11-02 | 2025-11-09 | 7 | 246 | 7
Phase 6: Refactoring | Refactor All Controllers | 2025-11-09 | 2025-11-16 | 7 | 253 | 7
Phase 6: Refactoring | Fix Database Issues | 2025-11-16 | 2025-11-19 | 3 | 260 | 3
Phase 6: Refactoring | Final Verification | 2025-11-20 | 2025-11-23 | 3 | 264 | 3
Phase 7: Deployment | Production Deployment | 2025-11-09 | 2025-11-16 | 7 | 253 | 7
Phase 7: Deployment | Academic Report Writing | 2025-11-16 | 2025-11-23 | 7 | 260 | 7
Phase 7: Deployment | Technical Documentation | 2025-11-23 | 2025-11-26 | 3 | 267 | 3
Phase 7: Deployment | Presentation Preparation | 2025-11-23 | 2025-11-30 | 7 | 267 | 7
Phase 7: Deployment | Final Submission | 2025-11-29 | 2025-11-30 | 1 | 273 | 1

## Legend
Phase | Color
Phase 1: Research & Requirements | Orange/Peach
Phase 2: System Design | Light Blue
Phase 3: Backend Implementation | Light Purple
Phase 4: Frontend Development | Light Green
Phase 5: Testing & QA | Light Yellow
Phase 6: MVC Refactoring | Light Red
Phase 7: Deployment & Docs | Light Cyan

## Project Info
Project Name | UniLearn/EduLearn - Learning Management System
Student ID | GCS220124
Greenwich ID | 001322934
Project Duration | 40 weeks (280 days)
Start Date | March 1, 2025
End Date | November 29, 2025
Total Phases | 7
Total Tasks | 42
Live URL | https://x.huy.global/
GitHub | https://github.com/givhvy/FINAL-PROJECT
Phase Breakdown
Phase 1: Research & Requirements | 6 weeks (March 1 - April 12)
Phase 2: System Design | 8 weeks (April 13 - June 7)
Phase 3: Backend Implementation | 11 weeks (June 8 - August 23)
Phase 4: Frontend Development | 11 weeks (August 24 - November 8)
Phase 5: Testing & QA | 7 weeks (October 5 - November 22)
Phase 6: MVC Refactoring | 5 weeks (October 19 - November 22)
Phase 7: Deployment & Docs | 3 weeks (November 9 - November 29)