## Gantt Timeline
UniLearn/EduLearn Project Timeline - Gantt Chart
|  |  |  | Mar 2025 |  |  |  |  | Apr 2025 |  |  |  | May 2025 |  |  |  |  | Jun 2025 |  |  |  | Jul 2025 |  |  |  | Aug 2025 |  |  |  |  | Sep 2025 |  |  |  | Oct 2025 |  |  |  | Nov 2025
Phase | Task Name | Start | Weeks | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40
Phase 1 | Literature Review | 03/01 | 2.0
Phase 1 | Competitive Analysis | 03/08 | 2.0
Phase 1 | Requirements Gathering | 03/15 | 2.0
Phase 1 | Use Case Development | 03/22 | 3.0
Phase 2 | Architecture Design | 04/13 | 2.0
Phase 2 | Database Schema Design | 04/20 | 3.0
Phase 2 | UI/UX Design | 05/04 | 3.0
Phase 2 | API Endpoint Design | 05/18 | 3.0
Phase 2 | Integration Planning | 05/25 | 2.0
Phase 3 | Dev Environment Setup | 06/08 | 1.0
Phase 3 | Authentication System | 06/15 | 2.0
Phase 3 | Core Models Development | 06/22 | 3.0
Phase 3 | Business Logic Controllers | 07/06 | 3.0
Phase 3 | Advanced Features | 07/20 | 3.0
Phase 3 | Payment Integration | 08/03 | 3.0
Phase 3 | Community Features | 08/10 | 2.0
Phase 3 | Media Upload Integration | 08/17 | 1.0
Phase 4 | Landing & Auth UI | 08/24 | 2.0
Phase 4 | Course Catalog & Details | 09/07 | 2.0
Phase 4 | Dashboard Interfaces | 09/14 | 3.0
Phase 4 | Lesson & Quiz Interfaces | 09/28 | 3.0
Phase 4 | Payment & E-commerce | 10/12 | 2.0
Phase 4 | Community & Profile | 10/19 | 2.0
Phase 4 | UI/UX Polish | 10/26 | 2.0
Phase 5 | Unit Testing | 10/05 | 3.0
Phase 5 | Integration Testing | 10/19 | 2.0
Phase 5 | Security Testing | 10/26 | 2.0
Phase 5 | Performance Testing | 11/02 | 2.0
Phase 5 | Cross-browser Testing | 11/09 | 2.0
Phase 5 | User Acceptance Testing | 11/16 | 1.0
Phase 6 | Create Firebase Helpers | 10/19 | 1.0
Phase 6 | Build Missing Models | 10/26 | 1.0
Phase 6 | Enhance Existing Models | 10/26 | 2.0
Phase 6 | Fix N+1 Query Problems | 11/02 | 1.0
Phase 6 | Refactor All Controllers | 11/09 | 1.0
Phase 6 | Fix Database Issues | 11/16 | 0.5
Phase 6 | Final Verification | 11/20 | 0.5
Phase 7 | Production Deployment | 11/09 | 1.0
Phase 7 | Academic Report Writing | 11/16 | 1.0
Phase 7 | Technical Documentation | 11/23 | 0.5
Phase 7 | Presentation Preparation | 11/23 | 1.0
Phase 7 | Final Submission | 11/29 | 0.2

## Legend
UniLearn/EduLearn Project
Project Timeline Legend
Phase | Description
Phase 1 | Research & Requirements Analysis (6 weeks)
Phase 2 | System Design (8 weeks)
Phase 3 | Backend Implementation (11 weeks)
Phase 4 | Frontend Development (11 weeks)
Phase 5 | Testing & QA (7 weeks)
Phase 6 | MVC Refactoring (5 weeks)
Phase 7 | Deployment & Documentation (3 weeks)